## Master
Task name | Hours | total
Make the website | 10 | 27
Database set up | 6
API set up | 5
Code for app | 6

## Sheet4
tasks | hours | Total hours
Set up APIs | 10
Set up Database | 3
Build login page | 3
build landing page | 2
build profile page | 4
build saved results page | 3
build page to discover songs/movies | 6
31

## David White Task Breakdown
Num tasks | Task name | Time in hours | total
| Set up DBs | 5 | 27
| build queries to add user information | 2
| build queries to edit user information | 1
| Get third party API keys | 1
| Set up Oath | 2
| Build login page | 2
| set up API calls to get user location | 1
| process user location | 1
| API calls to get and process movies/songs | 3
| queries to save results to a database | 2
| build page to allow the user to browser and select results | 3
| build user profile page | 2
| build save results page | 1
| queries to delete results from list | 1

## Norwich
Notes | Tasks | Hours | Total Hours
Pages need to build: - log in page - home page - profile page - result page - saved results page | Create Website | 8 | 29.25
Just need user name from auth and location information, favorite music genre | DB creation and user auth | 8
Need to parse json for API | Configuring API | 5
| Storing user data | 5
Pregenerate to save speed | Pregenerating movie/music list | 0.25
Random return | Query suggestion based on user data | 3
--Optional--
| Make it look presentable | 4 | 10
If not provided | Hosting, server configuration, domain | 6